## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Notes Application Testing
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | Gandham Swetha
Approved By:
SCOPE
Features to be Tested:
UI login validation
Create note through UI
Verify note appears instantly in UI
API GET /notes functionality
API DELETE note functionality
UI → API data validation (note created in UI appears in API)
API → UI validation (deleted note disappears in UI)
Data comparison between UI and API (Title, Description, Category)
Negative testing (invalid login, invalid API requests)
TESTING TYPE
Functional Testing | Done
Regression Testing | Done
Integration Testing | Done
UAT | Done
Environment: | QA(Quality Assurance)
Browser/OS: | Chrome/Windows 10
TIMELINE
Start Date: | 2026-05-04
End Date: | 2026-05-06
RESOURCES
QA Lead: | Gandham Swetha
QA Resources: | Gandham Swetha
Test Data Provider: | QA Team
RISKS & ASSUMPTIONS
Risks: | API response delays, environment downtime, UI synchronization issues
Assumptions: | Test environment and APIs will be available throughout testing

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | User Login | Validate successful login with valid credentials | User account exists
SC-002 | Create Note | Validate creating a new note through UI | User logged into Notes application
SC-003 | Instant Note Display | Validate newly created note appears instantly in UI | Note created successfully
SC-004 | Get Notes API | Validate GET /notes API returns notes list | API authentication available
SC-005 | UI to API Validation | Validate UI-created note appears in API response | Note created through UI
SC-006 | Delete Note API | Validate deleting note through API | Existing note available
SC-007 | API to UI Sync | Validate deleted note disappears from UI | Note deleted through API
SC-008 | Negative Validation | Validate invalid UI inputs and API requests | Application and API accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result |  | Priority | Status
TC-001 | SC-001 | Login with valid credentials | User account exists | 1. Enter valid username 2. Enter valid password 3. Click Login | User logged in successfully | Login successful | High | Pass
TC-002 | SC-001 | Login with invalid password | User account exists | 1. Enter valid username 2. Enter invalid password 3. Click Login | Error message displayed | Incorrect email address or password | High | Pass
TC-003 | SC-001 | Login with empty fields | Login page opened | 1. Leave fields empty 2. Click Login | Validation message displayed | A valid email address is required | Medium | Pass
TC-004 | SC-002 | Create note with valid details | User logged into application | 1. Click Add Note 2. Enter title and description 3. Click Save | Note created successfully | Notes successfully retrieved | High | Pass
TC-005 | SC-002 | Create note with empty title | User logged into application | 1. Click Add Note 2. Leave title empty 3. Click Save | Validation message displayed | Title is required | Medium | Pass
TC-006 | SC-003 | Validate note appears instantly in UI | Note created successfully | 1. Create note 2. Observe notes list | New note displayed instantly without refresh | successfully note appears | Medium | Pass
TC-007 | SC-003 | Validate multiple notes display correctly | Multiple notes created | 1. Create multiple notes 2. Check notes list | All notes displayed correctly | all notes appears | Medium | Pass
TC-008 | SC-004 | Validate GET /notes API returns status 200 | API access available | 1. Send GET /notes request | API returns status code 200 | "success": true, "status": 200, "message": "Notes successfully retrieved" | High | Pass
TC-009 | SC-004 | Validate GET /notes API response time | API access available | 1. Send GET /notes request 2. Measure response time | Response time less than 2 seconds | API response received in 1.42 seconds, which is within the expected limit | Medium | Pass
TC-010 | SC-005 | Validate UI-created note appears in API | Note created via UI | 1. Create note in UI 2. Call GET /notes API | Created note available in API response | "success": true, "status": 200, "message": "Notes successfully retrieved" | High | Pass
TC-011 | SC-005 | Validate UI and API note data match | Note created via UI | 1. Capture UI note details 2. Compare with API data | UI and API note details should match | "title": "Gardening", "description": "Cutting waste plants, Watering the plants", "category": "Home", | High | Pass
TC-012 | SC-006 | Delete note through API | Existing note available | 1. Send DELETE request 2. Verify response | Note deleted successfully | "success": true, "status": 200, "message": "Note successfully deleted" | High | Pass
TC-013 | SC-006 | Validate deleted note removed from API | Note deleted through API | 1. Delete note 2. Call GET /notes API | Deleted note not present in API | successfully note deleted by API | High | Pass
TC-014 | SC-007 | Validate deleted note disappears from UI | Note deleted through API | 1. Refresh UI 2. Check notes list | Deleted note not displayed in UI | deleted not is disappeared | High | Pass
TC-015 | SC-008 | Validate invalid API request handling | API server available | 1. Send invalid API request 2. Verify error response | Proper error message and status code displayed | "success": false, "status": 401, "message": "Access token is not valid or has expired, you will need to login" | Medium | Pass

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Username: swethagandham2003@gmail.com Password: Swetha@2003 | Valid login scenarios
TD-002 | Invalid User | Username: swethagandham2003@gmail.com Password: Wrong@123456 | Negative login test cases
TD-003 | Note Data | Title: Meeting Notes Description: Project discussion updates | Note creation scenarios
TD-004 | API Authentication Data | Email: swethagandham2003@gmail.com Token:12345678 | API authentication testing
TD-005 | Multiple Notes Data | Note1: Task List Note2: Daily Updates | Multiple note validation
TD-006 | Empty Note Data | Title: Empty Description: Empty | Validation and negative testing
TD-007 | Long Text Data | Title: Long Note Title Description: 500+ character content | Boundary value testing
TD-008 | Special Character Data | Title: @#$%^&* Note Description: Special characters validation | Input validation testing
TD-009 | Delete Note Data | Note ID: N101 Title: Temporary Note | API delete note scenarios
TD-010 | Invalid API Request Data | Invalid Endpoint: /notes/invalid | API negative testing

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Login with valid credentials | Gandham Swetha | 2026-05-05 | Pass |  | Executed successfully
TC-002 | Cycle-1 | Login with invalid password | Gandham Swetha | 2026-05-05 | Fail | DEF-001 | Error message not displayed
TC-003 | Cycle-1 | Create note with valid details | Gandham Swetha | 2026-05-05 | Pass |  | Note created successfully
TC-004 | Cycle-1 | Create note with empty title | Gandham Swetha | 2026-05-05 | Fail | DEF-002 | Validation message missing
TC-005 | Cycle-1 | Validate note appears instantly in UI | Gandham Swetha | 2026-05-05 | Pass |  | UI updated correctly
TC-006 | Cycle-1 | Validate multiple notes display correctly | Gandham Swetha | 2026-05-05 | Pass |  | Multiple notes displayed
TC-007 | Cycle-1 | Validate GET /notes API returns status 200 | Gandham Swetha | 2026-05-05 | Pass |  | API working as expected
TC-008 | Cycle-1 | Validate GET /notes API response time | Gandham Swetha | 2026-05-05 | Fail | DEF-003 | Response time exceeded 2 seconds
TC-009 | Cycle-1 | Validate UI-created note appears in API | Gandham Swetha | 2026-05-05 | Pass |  | Data matched successfully
TC-010 | Cycle-1 | Validate UI and API note data match | Gandham Swetha | 2026-05-05 | Pass |  | No mismatch found
TC-011 | Cycle-2 | Delete note through API | Gandham Swetha | 2026-05-05 | Pass |  | Note deleted successfully
TC-012 | Cycle-2 | Validate deleted note removed from API | Gandham Swetha | 2026-05-05 | Pass |  | Deleted note not found in API
TC-013 | Cycle-2 | Validate deleted note disappears from UI | Gandham Swetha | 2026-05-05 | Fail | DEF-004 | Deleted note still visible in UI
TC-014 | Cycle-2 | Validate invalid API request handling | Gandham Swetha | 2026-05-05 | Pass |  | Proper error message displayed
TC-015 | Cycle-2 | Login with empty fields | Gandham Swetha | 2026-05-05 | Pass |  | Validation messages displayed correctly

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
REQ-001 | TC-001, TC-002, TC-003 | User should be able to login using correct username and password details | Covered | Complete
REQ-002 | TC-004, TC-005 | User should be able to create a note and save it successfully | Covered | Complete
REQ-003 | TC-006, TC-007 | Newly created notes should be displayed immediately in the notes list | Covered | Complete
REQ-004 | TC-008, TC-009 | Notes API should return all available notes with proper response time | Covered | Complete
REQ-005 | TC-010, TC-011 | Notes created from UI should match the data shown in API response | Covered | Complete
REQ-006 | TC-012, TC-013 | User should be able to delete notes using API request | Covered | In Progress
REQ-007 | TC-014 | Deleted notes should not be visible in the UI after refresh | Covered | In Progress
REQ-008 | TC-015 | Application should display proper error message for invalid API requests | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-002 | Error message not displayed | User entered wrong password but no error message appeared on the screen | High | High | Open | Dev-User1 | 2026-05-05 | Needs investigation
DEF-002 | TC-005 | Validation message missing | Note was saved even after keeping the title field empty | Medium | High | Open | Dev-User2 | 2026-05-05 | Validation check required
DEF-003 | TC-009 | API response delay | Notes API is taking more time than expected to load the response | Medium | Medium | In Progress | Dev-User3 | 2026-05-05 | Performance optimization in progress
DEF-004 | TC-014 | Deleted note still visible in UI | Deleted note is still showing in the notes list after refreshing the page | High | High | Open | Dev-User1 | 2026-05-05 | UI sync issue

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes Application Testing
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | Gandham Swetha
EXECUTION SUMMARY
Total Test Cases: | 15
Test Cases Executed: | 15
Test Cases Passed: | 11
Test Cases Failed: | 4
Pass Percentage: | 0.733
73.3%
DEFECT SUMMARY
Total Defects: | 4
Critical Defects: | 0
High Defects: | 2
Medium Defects: | 1
Low Defects: | 1
Open Defects: | 3
Closed Defects: | 1
CONCLUSION
Testing Status: | In Progress
Release Readiness: | Pending Defect Resolution
Overall Recommendation: | Not Ready for Production
REMARKS | Login and note creation features are working properly.
Some validation messages are missing in few scenarios.
Deleted notes are still visible in UI after refresh.
API response time issue needs improvement.
Retesting is required after fixing open defects.